## Slide 1: 2025-26 Webinar series Status report

## Slide 2: Ofa webinar series
Webinars #1-4 Combined Data
475 Views on YouTube (and growing)
90 Live Attendees
135+ Registrants
Key Takeaways
There is interest in OFA webinars, both from speakers and audiences
  Positions OFA as a thought leader in the industry
  Keeps OFA top of mind for members
  Channel for a regular drumbeat of news
OnDemand views are growing on YouTube
Recorded webinars provide content to promote on OFA website and OFA LinkedIn page
Recommendations
Recommend extending webinar series support with Nereus and adding Webex Webinars feature to streamline registration
  Thank you to Ken for developing a system for registration using our existing Webex subscription and the OFA website; it has worked for now, but we recommend taking the next step and moving to Webex Webinars now that we have proven there is interest in sustaining the program
Board Request
Approve Webex Webinars subscription ($675/year)
Approve renewal of Nereus webinar support for additional 6-part webinar series for 2026-2027 ($13,500)

## Slide 3: Backup

## Slide 4: OFA Webinar Series at-a-glance
Webinar | Topic | Speaker(s) | Kick-off Date | Webinar Airdate
June 2025 COMPLETED! | Libfabric & UEC | Jianxin Xiong | w/o May 12 | Thursday, June 26
August 2025 COMPLETED | Coding to libfabric | Alexia Ingerson | w/o July 7 | Wednesday, August 27
October 2025 COMPLETED | - Sunfish - SC25 preview | Russ Herrell, Brian Pan | w/o September 1 | Thursday, October 23
November 2025 COMPLETED | Slingshot/UET | Keith Underwood | w/o October 20* | Wednesday, November 12th
February 2026 | Flux | Will Hobbs and Nate Hanford | w/o January 26, 2026 | Wednesday, February 25 at 10am PT
April 2026 | TBD | TBD | w/o March 9, 2026 | Thursday, April 23, 2026
Notes: Others
Partner
Sponsor

## Slide 5: Workback schedule
Week 1
Confirm speakers
Finalize webinar air date
Send calendar invitation placeholder
Request all speaker bios/headshots for webinar landing page
Create Webex Webinar landing page
Week 2
Open registration
Add webinar information to OFA website
Round 1 of promotions
Week 3
Marketing promotions (shareable LinkedIn posts, email promotions to members and leads, liaison co-marketing, etc.)
Webinar slides due for review
Week 4
Marketing promotions (shareable LinkedIn posts, email promotions to members and leads, liaison co-marketing, etc.)
Week 5
Marketing promotions cont.
Dry-run with speakers
Week 6
Marketing promotions cont.
Attendee reminder
Webinar airs

## Slide 6: OFA Webinar program
Nereus SOW
Platform Management
Program Management
Speaker Support
Material Review
Project Management
Promotion Content and Distribution
Audience Communications (Reminders, etc.)
Request for OFA Board to Approve Webinar Program Extension
Expenses | Option 1 Frequency: Bi-monthly Total: 6 webinars/year
Nereus | $13,500/year
WebEx Webinar Platform | $675/year
Total | $14,175
Notes: OFA Board approved April 17, 2025