## Sheet1
Task Name | February 21-26 | February 27-March 5 | March 6-March 12 | March 13-March-19 | October 31-November 6 | November 7-12 | November 13-18
Zephyr Northbound Interface Details
Transactional interface to provide Fabric Attached components/resources | Transactional interface to provide Fabric Attached components/resources | Transactional interface to provide Fabric Attached components/resources | Transactional interface to provide Fabric Attached components/resources | Transactional interface to provide Fabric Attached components/resources | Transactional interface to provide Fabric Attached components/resources
Resource characteristics, type of resource, address range, UUID, serial number | Resource characteristics, type of resource, address range, UUID, serial number | Resource characteristics, type of resource, address range, UUID, serial number | Resource characteristics, type of resource, address range, UUID, serial number
NetworkX to communicate wiring topology | NetworkX to communicate wiring topology | NetworkX to communicate wiring topology | NetworkX to communicate wiring topology
Eventing mechanism to request changes to the fabric---pulling | Eventing mechanism to request changes to the fabric---pulling | Eventing mechanism to request changes to the fabric---pulling | Eventing mechanism to request changes to the fabric---pulling
Zephyr Agent
Parse and punch into a database to allow agent to interact with the data | Parse and punch into a database to allow agent to interact with the data | Parse and punch into a database to allow agent to interact with the data | Parse and punch into a database to allow agent to interact with the data
Identify whata is important for functionality | Identify whata is important for functionality | Identify whata is important for functionality | Identify whata is important for functionality
|  |  | Agent query Zephyr calls | Agent query Zephyr calls | Agent query Zephyr calls | Agent query Zephyr calls
Translation tables | Translation tables | Translation tables | Translation tables
NetworkX file ingestion | NetworkX file ingestion | NetworkX file ingestion | NetworkX file ingestion
Conversion from Zephyr to Redfish/Swordfish | Conversion from Zephyr to Redfish/Swordfish | Conversion from Zephyr to Redfish/Swordfish | Conversion from Zephyr to Redfish/Swordfish | Conversion from Zephyr to Redfish/Swordfish | Conversion from Zephyr to Redfish/Swordfish | Conversion from Zephyr to Redfish/Swordfish
|  |  |  | Import Redfish/Swordfish | Import Redfish/Swordfish | Import Redfish/Swordfish
|  |  |  | Tranlastion to Zephyr API | Tranlastion to Zephyr API | Tranlastion to Zephyr API
Redfish/Swordfish interface representation
Redfish/Swordfish extensions for OFMF | Redfish/Swordfish extensions for OFMF | Redfish/Swordfish extensions for OFMF
Client requested changes to fabric sent to Zephyr | Client requested changes to fabric sent to Zephyr | Client requested changes to fabric sent to Zephyr | Client requested changes to fabric sent to Zephyr | Client requested changes to fabric sent to Zephyr
Redfish/Swordfish Emulator
OFMF level Emulator Post and Gets | OFMF level Emulator Post and Gets | OFMF level Emulator Post and Gets | OFMF level Emulator Post and Gets | OFMF level Emulator Post and Gets
OFMF memory chunk manipulator | OFMF memory chunk manipulator | OFMF memory chunk manipulator | OFMF memory chunk manipulator | OFMF memory chunk manipulator | OFMF memory chunk manipulator
OFMF connection manipulator | OFMF connection manipulator | OFMF connection manipulator | OFMF connection manipulator | OFMF connection manipulator | OFMF connection manipulator
GUI
Strip out unnecessary items | Strip out unnecessary items
|  | Establish what to put into display | Establish what to put into display
|  |  |  | Code display to match PoC available memory chunks | Code display to match PoC available memory chunks
Code display to match PoC connected memory chunks
[5 empty] | Modification of connections | Modification of connections
|  |  |  | Code display to match PoC connections | Code display to match PoC connections
[5 empty] | Modification of memory chunks | Modification of memory chunks
|  |  |  | Code display to match PoC endpoints | Code display to match PoC endpoints
OFA Workshop 2022
SC21 OFA Booth Details
Booth Workers | Booth Workers | Booth Workers | Booth Workers
Layout of Booth
Remote Demo site | Remote Demo site | Remote Demo site | Remote Demo site | Remote Demo site
|  | Demo details | Demo details
|  | On site Demo networking and cabling options---WiFi | On site Demo networking and cabling options---WiFi
|  | On site dieplays | On site dieplays
OFA Website
|  |  |  | Update OFA website with SC21 PoC details | Update OFA website with SC21 PoC details | Update OFA website with SC21 PoC details
|  |  |  | Update OFA website with SC21 BoF details | Update OFA website with SC21 BoF details | Update OFA website with SC21 BoF details
|  |  |  | Update OFA website with information on Redfish | Update OFA website with information on Redfish | Update OFA website with information on Redfish
|  |  |  | Update OFA website with information on Swordfish | Update OFA website with information on Swordfish | Update OFA website with information on Swordfish
|  |  |  | Update OFA website on links to GitHub | Update OFA website on links to GitHub | Update OFA website on links to GitHub
|  |  |  | How to for Redfish/Swordfish Emulator | How to for Redfish/Swordfish Emulator | How to for Redfish/Swordfish Emulator
|  |  |  | Update Use Cases | Update Use Cases | Update Use Cases
|  |  |  | SodaConn links and description | SodaConn links and description | SodaConn links and description
|  |  |  | Gen-Z Coffee Talk links and description | Gen-Z Coffee Talk links and description | Gen-Z Coffee Talk links and description
|  |  |  | Snia talks and description | Snia talks and description | Snia talks and description
|  |  |  | OFA Workshop Links and description | OFA Workshop Links and description | OFA Workshop Links and description